## Daily
GRANTT CHART TEMPLATE
o | Project Name | : | Product Launching Event
o | Project Description | : | Launching New Phone Product
o | Project Length | :
o | Start Date | : | 2009-07-01 | TRUE | End Date | 2009-08-01
|  |  |  | FALSE | Number of Weeks | 5 | 5
o | Working Days | : | Monday - Friday | 1
o | Today's Marker | : | Yes | 1
o | Holiday's Marker | : | Yes | 1
Level | Task |  |  | PIC |  | Start Date | Finish Date | WD | DC | DR | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5
[16 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 |  | #VALUE!
[11 empty] | 1 | 6/29/09 | [5 empty] | 2 | 7/6/09 | [5 empty] | 3 | 7/13/09 | [5 empty] | 4 | 7/20/09 | [5 empty] | 5 | 7/27/09 | [6 empty] | #VALUE!
[11 empty] | 2009-06-29 | 2009-06-30 | 2009-07-01 | 2009-07-02 | 2009-07-03 | 2009-07-04 | 2009-07-05 | 2009-07-06 | 2009-07-07 | 2009-07-08 | 2009-07-09 | 2009-07-10 | 2009-07-11 | 2009-07-12 | 2009-07-13 | 2009-07-14 | 2009-07-15 | 2009-07-16 | 2009-07-17 | 2009-07-18 | 2009-07-19 | 2009-07-20 | 2009-07-21 | 2009-07-22 | 2009-07-23 | 2009-07-24 | 2009-07-25 | 2009-07-26 | 2009-07-27 | 2009-07-28 | 2009-07-29 | 2009-07-30 | 2009-07-31 | 2009-08-01 | 2009-08-02
1 | Product Package Design |  |  | Marketing Dept |  | 2009-07-01 | 2009-07-08 | 6 | 1751 | -1745
1.1 | Define Brand Name |  |  | John |  | 2009-07-01 | 2009-07-02 | 2 | 1751 | -1749
1.2 | Box Cover Design |  |  | John |  | 2009-07-03 | 2009-07-08 | 4 | 1749 | -1745
1.3 | User Guide Cover Design |  |  | Jane |  | 2009-07-03 | 2009-07-08 | 4 | 1749 | -1745
1.4 | Warranty Card Design |  |  | Jane |  | 2009-07-03 | 2009-07-08 | 4 | 1749 | -1745
2 | Marketing Kit |  |  | Marketing Dept |  | 2009-07-09 | 2009-07-17 | 7 | 1745 | -1738
2.1 | Brochures |  |  | Steve |  | 2009-07-09 | 2009-07-17 | 7 | 1745 | -1738
2.2 | Banners |  |  | Steve |  | 2009-07-09 | 2009-07-17 | 7 | 1745 | -1738
3 | Event |  |  | Public Relation Dept |  | 2009-07-01 | 2009-07-20 | 14 | 1751 | -1737
3.1 | Define Location |  |  | Jenny |  | 2009-07-01 | 2009-07-08 | 6 | 1751 | -1745
3.2 | Book Location |  |  | Jenny |  | 2009-07-08 | 2009-07-08 | 1 | 1746 | -1745
3.3 | Press Conference |  |  | Marry |  | 2009-07-20 | 2009-07-20 | 1 | 1738 | -1737