## IT Project Gantt Chart
IT PROJECT GANTT CHART TEMPLATE
[ Project Name ]
TASK NAME | START DATE | END DATE | DURATION (days)
Planning | 2022-01-16 | 2022-01-21 | 6
Wireframes | 2022-01-22 | 2022-01-23 | 2
Image Sourcing | 2022-01-22 | 2022-01-28 | 7
Graphics | 2022-01-27 | 2022-01-29 | 3
Design | 2022-01-28 | 2022-02-04 | 8
Search Incorporation | 2022-02-05 | 2022-02-09 | 5
Standards | 2022-01-28 | 2022-02-05 | 9
Legal | 2022-02-04 | 2022-02-06 | 3
Testing | 2022-02-07 | 2022-02-10 | 4
Optimization | 2022-02-09 | 2022-02-12 | 4
Platform Adaptation | 2022-02-11 | 2022-02-14 | 4
App Development | 2022-02-15 | 2022-02-17 | 3
Marketing | 2022-01-28 | 2022-02-05 | 9
Rollout | 2022-02-04 | 2022-02-06 | 3
Documentation | 2022-02-07 | 2022-02-10 | 4
Task 16 | 2022-02-09 | 2022-02-12 | 4
Task 17 | 2022-02-11 | 2022-02-14 | 4
Task 18 | 2022-02-15 | 2022-02-17 | 3
Task 19 | 2022-02-11 | 2022-02-14 | 4
Task 20 | 2022-02-15 | 2022-02-17 | 3
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description
MILESTONE 5:
00/00/00
Brief Description
MILESTONE 4:
00/00/00
Brief Description

## IT Project Gantt Chart BLANK
IT PROJECT GANTT CHART TEMPLATE
[ Project Name ]
TASK NAME | START DATE | END DATE | DURATION (days)
Planning |  |  | 1
Wireframes |  |  | 1
Image Sourcing |  |  | 1
Graphics |  |  | 1
Design |  |  | 1
Search Incorporation |  |  | 1
Standards |  |  | 1
Legal |  |  | 1
Testing |  |  | 1
Optimization |  |  | 1
Platform Adaptation |  |  | 1
App Development |  |  | 1
Marketing |  |  | 1
Rollout |  |  | 1
Documentation |  |  | 1
Task 16 |  |  | 1
Task 17 |  |  | 1
Task 18 |  |  | 1
Task 19 |  |  | 1
Task 20 |  |  | 1
MILESTONE 1:
00/00/00
Brief Description
MILESTONE 2:
00/00/00
Brief Description
MILESTONE 3:
00/00/00
Brief Description
MILESTONE 5:
00/00/00
Brief Description
MILESTONE 4:
00/00/00
Brief Description
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.