## Info
Project Workbook Information
The project workbook allows project managers, team members, sponsors, and stakeholders to easily track and monitor project activities. Any of these worksheets can easily be broken out into separate documents.
Suggested Sheets for All Projects
Data | Filling out the Data sheet completes the header portion of all remaining sheets in the project workbook.
Minicharter | The Project Minicharter sheet can be used as a charter for small projects or a summarization of a full charter for larger projects.
Stoplight | The Stoplight Report sheet contains a status report that can be used to keep sponsors, team members, and stakeholders informed of project progress.
Budget | The Budget sheet allows you to track original budget, expenditures to date, and any cost variance.
CBA | The Cost/Benefit Analysis sheet allows you to review the proposed project and potential alternatives and make a project selection based on a greater ROI (return on investment).
Risks | The Risk Management Matrix sheet allows you to identify, qualify, quantify, and prioritize risks (events that might happen; the uncertainty of a project), create mitigation and contingency plans, and assign risks owners.
Issues | The Issues Log sheet allows you to identify and monitor project issues (unplanned events that have happened).
Action | The Action Items sheet allows you to track and monitor action items assigned to team members. Action items are tasks that must be done but are too insignificant from a time perspective to track in your project schedule.
Miles | The Deliverable Milestones sheet allows you to identify major deliverable milestones and the due dates, objectives, assumptions, and constraints relevant to that deliverable milestone.
WBS | The Work Breakdown Structure sheet includes the activities that must be completed during a project, the effort required, all relevant dates, and the resources assigned to do the work.
Roster | The Roster sheet provides contact information for all those involved on the project.
R&R | The Roles and Responsibilities sheet shows the primary role of team members, any deliverables in which they are involved, and the percentage of time they are expected to work on the project.
RAM | The Resource Assignment Matrix sheet shows you what type of resource is responsible for, or somehow involved with, each deliverable. The tasks listed are samples; you should update the RAM with tasks appropriate for your project.
RCM | The Resource Commitment Matrix sheet shows how many effort hours each person on the project has been allocated by month.
A&C | The Assumptions and Constraints sheet allows you to track project assumptions and constraints.
Decision | The Decision Log sheet allows you to track all major decisions made during the course of the project.
Comm | The Communication Plan sheet allows you to detail your communication plan: how you are going to communicate, whom you will be communicating with, how often, in what format, etc.
Stake | The Stakeholder Analysis sheet allows you to identify stakeholders, their role, and their requirements.
Expectations | The Expectations sheet allows you to identify and track the expectations of various stakeholders.
Chg Log | The Change Control Log sheet allows you to track all change requests that are in process or finalized.
Deliver | The Deliverable Acceptance Log sheet allows you to track the status of deliverable acceptances.
PERT | The PERT Analysis sheet allows you to perform PERT analysis on WBS tasks.
Delphi | The Delphi Exercise sheet allows you to develop estimates for WBS tasks through the Delphi technique.
TimeSum | The Timesheet Totals sheet allows you to track effort hours of your entire team by individual and by month.
Timesheet | The Timesheet can be used by each team member to submit effort hours by activity, by month.
Size Est | The Initial Project Size Estimate sheet allows you to estimate, at high-levels (40,000 ft. view), the size of a project. This estimate should not be considered final as requirements and technical specifications typically have not been fully developed yet.
Res Load | The Resource Loading sheet allows you to identify the work effort required, the duration, and the allowed commitment level of each person assigned to the project.
Qual Metrics | The Project Quality Metrics sheet allows you to identify critical success criteria, related quality metrics, and their priority.
Source: www.iappm.org

## Data
Project
Project #
Project manager
Sponsor
Project artifacts
Last updated

## Minicharter
Project Minicharter
Project |  | Project #
Project manager |  | Sponsor | 0
Project artifacts |  | Updated
Background
Business need and business benefits
Objectives
Scope | In Scope | Out of Scope
Deliverables | Deliverable | Due Date
Flexibility matrix | Scope
Schedule
Cost
Key considerations | Assumptions & Constraints | Risks
|  | Category | Risk Description
Success criteria | 1 -
2 -
3 -
4 -
5 -
Signatures
Sponsor
Signature
Printed name
Date
Project manager
Signature
Printed name
Date
Note on C16: Options are: Most flexible Moderately flexible Least flexible
Note on C17: Options are: Most flexible Moderately flexible Least flexible
Note on C18: Options are: Most flexible Moderately flexible Least flexible
Note on B19: Note A for assumptions, C for constraints
Note on C20: This is a field you can use to identify risks by categories such as technological, personnel, etc.

## Stoplight
Stoplight Report
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor | 0
Project artifacts | [5 empty] | Updated
Deliverables
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Schedule
Scope
Cost
Risk
Issues
Planned completion
Est. completion
Management Alert
ID | Situation Requiring Management Attention |  |  |  | Action Plan |  |  |  | Owner
Accomplishments During Reporting Period
ID | Description of Accomplishment |  |  | Planned Completion | Date Completed | Owner |  | Comments
Deliverables | Title/Description |  |  |  |  | Title/Description
1 |  |  |  |  | 6
2 |  |  |  |  | 7
3 |  |  |  |  | 8
4 |  |  |  |  | 9
5 |  |  |  |  | 10
Note on B8: Options are: Green: On schedule/on budget Yellow: Somewhat behind schedule/somewhat over budget Red: Behind schedule/over budget
Note on A28: In Row 7 there are 10 deliverables listed. This section allows you to explain each deliverable.

## Budget
Budget
Project |  | Project #
Project manager |  | Sponsor | 0
Project artifacts |  | Updated
Budget Status
Approved Budget | Planned Expenditures to Date | Actual Expenditures to Date | Variance
0 | 0 | 0 | 0
| Planned Remaining Budget | Actual Remaining Budget | Variance
| 0 | 0 | 0
Additional $ needed
Budget Details
Internal Expenses
Salaries | Hourly Rate | # Hours | Total Cost
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Other Internal Expenses |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total Internal Expenses |  |  |  | 0
External Expenses
Consulting Costs |  |  | Total Cost
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Capital Expenditures |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total External Expenses |  |  |  | 0
Total Budget |  |  |  | 0

## CBA
Cost/Benefit Analysis
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor | 0
Project artifacts |  |  |  | Updated
Project Development and Maintenance Costs
Description | FY01 | FY02 | FY03 | FY04 | FY05 | Total
Cost of Project Development
Salaries
Other internal expenses
Consulting costs
Capital expenditures
Total project costs | 0 | 0 | 0 | 0 | 0 | 0
Cost of Support
Operational costs
Nonrecurring costs
Recurring costs
Total ongoing support costs | 0 | 0 | 0 | 0 | 0 | 0
Benefits/Savings
Current Process | FY01 | FY02 | FY03 | FY04 | FY05 | Total
Total annual price
New Process
Total annual price
Annual savings | 0 | 0 | 0 | 0 | 0 | 0
Cumulative savings | 0 | 0 | 0 | 0 | 0 | 0
Cumulative costs | 0 | 0 | 0 | 0 | 0 | 0
Cumulative total net savings | 0 | 0 | 0 | 0 | 0 | 0
Future Value
Present Value | Interest Rate |  | # Periods |  | Future Value
0
Present Value
Future Value | Interest Rate |  | # Periods |  | Present Value
0 |  |  |  |  | 0
Net Present Value
Period | Cash Flow |  |  |  | Present Value
1
2
3
4
5
Totals | 0 |  |  |  | 0
Project development cost |  |  |  |  | 0
Net present value |  |  |  |  | 0
Example
Example
Note on A32: How much is the money worth today?
Note on D32: How many years will the project last?
Note on F32: This is how much money you expect the project to be worth.
Note on A36: This is how much money you expect the project to be worth.
Note on D36: How many years will it take until the company starts seeing this profit?
Note on F36: This is how much the money you project making would be worth in today's market.
Note on B40: FV for the period's return. Note: Change the PV # Periods to match the Period here.
Note on F40: This is how much the money you project making would be worth in today's market.

## Risks
Risk Management Matrix (Risk Register)
Project | [8 empty] | Project #
Project manager | [8 empty] | Sponsor | 0
Project artifacts | [8 empty] | Updated
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | What is this risk? |  |  |  | 0 |  | What act or event initiates either the risk occurrence or precipitates the response strategy? | How will you respond to this risk and what actions will you take to match that response? | If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround? | Who monitors this risk?
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
Note on C6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on I6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on L6: Options are: Open Closed

## Issues
Issues Log
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor | 0
Project artifacts |  |  |  | Updated
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | What is the issue? | How will this impact scope, schedule & cost? | How do you intend to deal with this issue? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on F6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Action
Action Items
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor | 0
Project artifacts |  |  |  |  | Updated
ID | Action Item | Owner | Status | Date Entered | Planned Completion | Actual Completion | Comments
1 | What is the item to be completed? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on D6: Options are: Open Closed

## Miles
CONSTRUCTION SCHEDULE
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor | 0
Project artifacts |  |  |  |  | Updated
ID | Milestone | Description | Planned Completion | Actual Completion | Objectives | Assumptions | Constraints
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## WBS
Work Breakdown Structure
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor | 0
Project artifacts | [5 empty] | Updated
ID | Task | Dependencies | Status | Effort Hours | Cost | Start Date | Planned Completion | Estimate to Completion | Actual Completion | Resource
1 |  | ID # of task
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on D6: Options are: Open Closed

## Roster
Roster
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor | 0
Project artifacts |  |  |  |  | Updated
Name | Core/ Extended Team | Title | Dept. | Phone | Cell Phone | E-Mail | Project Role
|  |  |  | 000.000.0000 | 000.000.0000

## R&R
Roles and Responsibilities
Project |  |  |  |  | Project #
Project manager |  |  |  |  | Sponsor | 0
Project artifacts |  |  |  |  | Updated
Name | Core/ Extended Team | % Assigned | Deliverables Leading | Deliverables Participating On | Project Role | Responsibility | Other Project Assignments

## RAM
Resource Assignment Matrix
Project | [6 empty] | Project #
Project manager | [6 empty] | Sponsor |  |  | 0
Project artifacts | [6 empty] | Updated
Project Task |  |  |  | Business End Users | Business Sponsor | IS Sponsor | Business Driver | Business Project Lead | Project Manager | Business Sys. Analyst | Data Modeler | DBA | Data Staging Designer | Educator | Appl'n Developer | Tech/Security Architect | Tech Support Specialist | Data Staging Programmer | Data Steward | QA Analyst
Project Management and Requirements
Initiation
1 |  |  | Develop preliminary project scope
2 |  |  | Identify business need
3 |  |  | Develop preliminary budget
4 |  |  | Identify preliminary return on investment
5 |  |  | Complete project charter
Planning
1 |  |  | Establish project identity
2 |  |  | Identify project team/resources
3 |  |  | Conduct stakeholder analysis
4 |  |  | Prepare draft project schedule
5 |  |  | Conduct project kickoff meeting
6 |  |  | Gather detailed user requirements
7 |  |  | Define current business processes (as is)
8 |  |  | Revise project schedule
9 |  |  | Develop project communication plan
10 |  |  | Develop project organizational structure
11 |  |  | Identify training plan
12 |  |  | Develop project quality plan
13 |  |  | Develop scope management plan
14 |  |  | Develop risk management plan
15 |  |  | Develop change management plan
16 |  |  | Develop cost management plan
17 |  |  | Develop schedule management plan
18 |  |  | Develop technical specifications
19 |  |  | Develop technical architecture
20 |  |  | Conduct project procurement
21 |  |  | Finalize project budget
22 |  |  | Finalize return on investment
23 |  |  | Ongoing project management
Execution
1 |  |  | Develop training materials
2 |  |  | Execute communication plan
3 |  |  | Develop software
4 |  |  | Develop new business processes (to be)
5 |  |  | Deploy new software
6 |  |  | Conduct training
Closing
1 |  |  | Get deliverable acceptance
2 |  |  | Close out contracts
3 |  |  | Finalize budget
4 |  |  | Finalize return on investment
5 |  |  | Conduct closure survey
6 |  |  | Conduct/document lessons learned
7 |  |  | Archive project
Legend
| Creates the deliverable |  |  | C1: primary creator; C2: contributor
| Input required |  |  | I
| Reviews the deliverable |  |  | R
| Approves the deliverable |  |  | A
| Notified when the deliverable is complete |  |  | N
| Owns the deliverable upon completion |  |  | O

## RCM
Resource Commitment Matrix
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor |  | 0
Project artifacts | [5 empty] | Updated
Effort Hours Committed
Names | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## A&C
Assumptions and Constraints
Project |  |  | Project #
Project manager |  |  | Sponsor | 0
Project artifacts |  |  | Updated
ID | Description | Comments | Type | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on D6: Options are: A: assumption C: constraint
Note on E6: Options are: Open Closed

## Decision
Decision Log
Project |  |  | Project #
Project manager |  |  | Sponsor | 0
Project artifacts |  |  | Updated
ID | Decision Description | Comments | Owner | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on D6: Who made the decision?
Note on E6: Options are: Open Closed

## Comm
Communication Plan
Project |  |  | Project #
Project manager |  |  | Sponsor | 0
Project artifacts |  |  | Updated
ID | Communication | Description | Frequency | Format | Owner | Recipient/ Attendees
1 | What type of communication is this? | What is the description of the contents/purpose of this communication? |  |  | Who sends? | Who gets?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Note on E6: Examples: E-mail Meeting
Note on B7: Examples: Executive status report Team status report

## Stake
Stakeholder Analysis
Project |  |  | Project #
Project Manager |  |  | Sponsor | 0
Project Artifacts |  |  | Updated
ID | Stakeholder | Role | Impact | Influence | Risk Tolerance | Needs | Responsibility
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on D6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on E6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low

## Expectations
Expectations
Project |  | Project #
Project manager |  | Sponsor |  | 0
Project artifacts |  | Updated
ID | Expectation Description | Source | Must Have | Want to Have | Nice to Have | Date Identified

## Chg Log
Change Control Log
Project | [5 empty] | Project #
Project Manager | [5 empty] | Sponsor | 0
Project Artifacts | [5 empty] | Updated
ID | Change Description | Priority | Originator | Date Entered | Date Assigned | Evaluator | Status | Date of Decision | Included in Rev. #
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on C6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on D6: Who identified the change needed?
Note on G6: Who will decide what action is taken on the change?
Note on H6: Options are: In review Rejected Deferred Approved
Note on J6: Options are: No Rev. #

## Deliver
Deliverable Acceptance Log
Project |  |  | Project #
Project manager |  |  | Sponsor | 0
Project artifacts |  |  | Updated
ID | Deliverable Description | Comments | Evaluator | Status | Date of Decision
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note on E6: Options are: In review Rejected Accepted

## PERT
PERT Analysis
Project | [7 empty] | Project #
Project Manager | [7 empty] | Sponsor |  | 0
Project Artifacts | [7 empty] | Updated
ID | Task | Most Likely | Min | Max | PERT Est | 15/15 Comp'ed Est | Std Dev | +1 Std Dev | -1 Std Dev | +2 Std Dev | -2 Std Dev | +3 Std Dev | -3 Std Dev
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Delphi
Delphi Exercise
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor |  | 0
Project artifacts | [5 empty] | Updated
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0 | #DIV/0!
Minimum | [8 empty] | 0 | #DIV/0!
Maximum | [8 empty] | 0 | #DIV/0!

## TimeSum
Timesheet Totals
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor |  | 0
Project artifacts | [5 empty] | Updated
Effort Hours Spent
Name | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Timesheet
Timesheet
Project | [5 empty] | Project #
Project manager | [5 empty] | Sponsor |  | 0
Project artifacts | [5 empty] | Updated
Name | Insert name here
Effort Hours Spent
Task | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Size Est
Initial Project Size Estimate
Project |  |  | Project #
Project manager |  |  | Sponsor | 0
Project artifacts |  |  | Updated
Scope Estimate
Technology Systems Impacted
|  | 1 to 2 | 3 to 5 | 6 or more
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
Benefit | Low |  |  | Avoid
Medium
| High | Automatically do; no approval needed

## Res Load
Resource Loading
Project |  |  | Project #
Project manager |  |  | Sponsor | 0
Project artifacts |  |  | Updated
Effort Hours Committed
ID | Names | Estimate of Total Effort | Activity Duration | Commitment Level | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total | 0 | 0 | 0 | 0

## Qual Metrics
Project Quality Metrics
Project |  |  | Project #
Project Manager |  |  | Sponsor | 0
Project Artifacts |  |  | Updated
ID | Critical Success Criteria | Potential Quality Metric |  | Priority | Metric Target | Action Plan