VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

JISC DEVELOPMENT PROGRAMMES Project Document Cover Sheet PROGRESS REPORT

Project

| Project Acronym |  | VERSIONS | Project ID |  |
| --- | --- | --- | --- | --- |
| Project Title |  | Versions of Eprints – user Requirements Study and Investigation of the |
|  |  | Need for Standards |  |  |
| Start Date |  | July 2005 | End Date | February 2007 |
| Lead Institution |  | London School of Economics and Political Science |
| Project Director |  | Jean Sykes, Librarian & Director of IT Services, LSE |
| Project Manager & |  | Frances Shipsey |  |  |
| contact details |  | British Library of Political and Economic Science, London School of |
|  |  | Economics and Political Science, 10 Portugal Street, London WC2A |
|  |  | 2HD. Tel: +44(0)20 7955 6915; Fax: +44(0)20 7955 7454; Email: |
|  |  | f.m.shipsey@lse.ac.uk |  |  |
| Partner Institutions |  | Nereus Project Consortium (www.nereus4economics.info) |
| Project Web URL |  | www.lse.ac.uk/versions |  |  |
| Programme Name (and |  | Digital Repositories Programme |  |
| number) |  |  |  |  |  |
| Programme Manager |  | Neil Jacobs |  |  |

Document

| Document Title | Progress Report |  |  |
| --- | --- | --- | --- |
| Reporting Period | February to July 2006 |  |  |
| Author(s) & project role | Frances Shipsey, Project Manager |  |
| Date | 16 August 2006 | Filename | VERSIONS Project Progress |
|  |  |  | Report Jul06 v0c.doc |
| URL | if document is posted on project web site |
| Access | 9 Project and JISC internal | General dissemination |

Document History

| Version | Date | Comments |
| --- | --- | --- |
| 0a | 11 August 2006 | Draft version sent to Programme Manager on 14 August 2006 |
| 0b | 14 August 2006 | Draft version sent to Project Director for comment |
| 0c | 16 August 2006 | Final draft version sent to VERSIONS Project Steering |
|  |  | Committee for approval |

Page 1 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

Overview of Project

Grant Statement

Please confirm that the project is being conducted under the terms agreed with JISC in the letter of grant and the JISC Terms and Conditions attached to it.

Note any changes to the original award, including any extensions or alterations granted.

The project is being conducted under the terms agreed with JISC in the letter of grant dated 13 May 2005 and in subsequently-agreed adjustments reported in the Progress Report for January 2006.

A further one month no-cost extension to the Project was agreed with the Programme Manager by email on 16 August 2006, so that the Project end date was adjusted from January 2007 to February 2007.

2. Aims and Objectives

Explain any changes to the original aims/objectives outlined in the project plan.

List the targets set for this reporting period and explain if they have been met.

There are no changes to the original aims and objectives outlined in the project plan.

Targets set for this reporting period were as follows:

| Target | Status |
| --- | --- |
| WP1: Project meetings | Met |
| WP1: Project telephone conference calls | Met |
| WP2: Interim findings report based on interviews |  |
| WP2: Develop questionnaire in light of interview findings and | Met |
| publications list analysis |  |
| WP2: Publicise and launch online questionnaire | Met |
| WP2: Develop scenarios from interviews | Met |
| WP2: Analyse results (of online surveys) including free text |  |
| comments |  |
| WP2: Report on findings of user study |  |
| WP3: Analysis of proportion of papers available in full text | Met |
| WP3: Project Team and Nereus EO partners provide further | Met |
| information about provenance and reasons for non- |  |
| availability |  |
| WP3: Consolidation of list and cross-tabulation with ROMEO | Met |
| listing |  |
| WP3: Analysis of findings | Met |
| WP3: Report on findings of publications list analysis |  |
| WP4: Literature review |  |
| WP4: Guidelines for versions |  |
| WP5: Workshop of stakeholders and report | Met |

3. Overall Approach

Explain any changes to the overall approach outlined in the project plan.

No changes have been made to the overall approach since the previous progress report.

Page 2 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

4. Project Outputs

Summarise progress during the reporting period and milestones/deliverables achieved. Please provide links to outputs where these are available online.

Progress during the reporting period has been steady though some activities have taken much longer than anticipated, notably the design of two questionnaires and the investigation of full text availability of Economists Online authors in six of the project partners’ repositories.

The following deliverables were completed during the reporting period:

WP2: the VERSIONS questionnaires were made available through a webpage on the VERSIONS

Project website: http://www.lse.ac.uk/library/versions/surveys.html

WP2: questions used in the surveys have been made available to Bristol Online Surveys (BOS) academic subscribers as examples of surveys produced using the survey software: www.survey.bris.ac.uk . The Project is grateful for the help of the BOS Support Team in facilitating this.

WP2: Scenarios were written and made available via the Project website and on the Digital

Repositories Programme wiki: http://www.lse.ac.uk/library/versions/scenarios.htm and http://www.ukoln.ac.uk/repositories/digirep/index/Scenarios_and_use_cases

WP5: An evaluation workshop was held at LSE in May 2006. The event gathered feedback from key stakeholders such as repository software developers, metadata experts and librarians/repository managers on the survey design and on the current thinking of the project regarding possible solutions to version identification in repositories. The notes of the workshop are available at: http://www.lse.ac.uk/library/versions/deliverables.html

5. Project Outcomes

Summarise achievement against objectives, list outcomes and findings to date, and any interim conclusions.

How do you see the project developing? Has progress changed the project in any way, and are there implications for the programme?

What lessons have been learned that could be passed on to other projects or applied elsewhere?

Through the completion of the interviews with researchers in February 2006 and the design and launch of the online survey which was conducted from May to July, the Project has made progress with finding out researchers’ requirements and current practices, though the results are still to be fully analysed and reported:

- understanding of different versions – a survey question on terminology used by researchers themselves to describe different revisions they make to papers and questions on the ways in which researchers manage and store their own revisions of their work have revealed useful information about researchers’ understanding of this process

- attitudes towards secure storage and open access availability of papers at different stages in the lifecycle –

- variations in requirements depending on specific stakeholder roles, eg journal editor, head of department – this should be capable of analysis as responses were received from 67 heads of department or research unit, 39 journal editors, 25 working paper series editors and 34 officers of learned society or research association

- existing repository use by researchers (both institutional and subject repositories) – survey questions showed that 33% of respondents have an institutional repository, 43% do not and 24% do not know. Of the 33% who were aware of their institution having a repository, 59% had placed papers in the repository. When asked whether researchers would place a copy of a final author version of their journal articles in a repository if invited to by their institution in future, 81% replied Yes.

Page 3 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

- Current practices among academic researchers in retention of their own authors’ versions – several questions in the survey were relevant here: responses to one question suggested that 91% of respondents do keep their final accepted versions of journal articles permanently. Researchers were also asked to describe how they manage their own files when revising their work and to say whether they are satisfied with their own systems – this was a popular question and should provide some useful tips for researchers for inclusion in the toolkit

Contact with both the RIVER Scoping Study (led by Rightscom) and the JISC Eprints Application Profile Working Group (led by Julie Allinson, UKOLN and Andy Powell, Eduserv) has been very useful and has helped to crystallise the Project’s tentative thinking about hierarchical representation and linking of bibliographic records in order to manage different versions. The Eprints Application Profile Working Group’s work on incorporating ideas from FRBR has taken this thinking forward very effectively.

It is looking likely that the Eprints Application Profile will therefore deal with some of the issues relating to representation of versions in bibliographic records and that through the Eprints Application Profile Working Group’s Deployment Plan, the Group’s recommendations will be implemented initially by three of the open source repository software development communities. This development may mean that for several of the proposed guidelines and standards from the VERSIONS Project it will be appropriate simply to refer to work of the Eprints Application Profile Working Group.

6. Stakeholder Analysis

Summarise the project’s engagement with stakeholders including users.

6.1 Project Partners

The Project has engaged with immediate project partners at Project Module meetings held as part of the Nereus Consortium meetings as follows:

May 2006, Oxford

In addition there was one telephone conference call held between partners during April 2006.

The jiscmail mailing lists set up for communications with project partners have been used to maintain contact. A monthly informal update has also been sent to Project partners and this are also made available on the Project website News page: http://www.lse.ac.uk/library/versions/news.html

6.2 JISC

The Project has been represented at the following JISC meeting:

JISC 2nd Digital Repositories Programme Meeting, Warwick, 27-28 March 2006

6.3 Other Digital Repositories Projects and Studies

The VERSIONS Project Manager along with one other LSE Library colleague were partners in the Scoping Study on Repository Version Identification (RIVER), commissioned by the JISC Scholarly Communications Group, led by Rightscom, with Oxford University Computing Services also as partners. This study was carried out from January to March 2006. There was a workshop held in Oxford in February 2006, at which the VERSIONS Project was represented. Scenarios from the VERSIONS Project were shared with the RIVER team. The final report is at: http://www.jisc.ac.uk/uploaded_documents/RIVER%20Final%20Report.pdf

The Project Manager joined the JISC Dublin Core Eprints Application Profile Working Group as a member during June-August 2006. She attended a Kick-Off Meeting, London, 5 June 2006 and contributed to the email discussion about the draft application profile thereafter. Early results from the VERSIONS online survey were shared with the Working Group.

Page 4 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

6.4 Users

The project has engaged with users during the reporting period by means of the online survey.

Responses were received from 464 academic researchers in 41 countries.

6.5 Other

The project engaged with stakeholders such as librarians, other university personnel and publishers by means of a separate online questionnaire. This attracted 133 responses from over 20 countries. Around half of the respondents to this survey were librarians/IT staff directly engaged with repositories. Others included researchers, university senior management, publishers, repository software developers, data or computing centre managers.

The Project also hosted a workshop during May with invited participants from stakeholder groups such as the library and repository software communities.

The Library of LSE is represented on the Journal Article Versions Review Group of the NISO/ALPSP Working Group on Versions of Journal Articles by the Library’s Information Services Manager. The VERSIONS Project Manager reviewed and discussed with the Information Services Manager draft documents produced by the NISO/ALPSP Group during March/April, prior to the Information Service Manager’s response to the Working Group.

7. Risk Analysis

Summarise any problems that have occurred and any mitigating actions taken.

There is nothing to report under this heading.

8. Standards

Note any changes in the standards to be used and the reasons.

There is nothing to report under this heading.

9. Technical Development

Note any changes in the development approach or technologies to be used and the reasons.

There is nothing to report under this heading.

10. Intellectual Property Rights

Summarise progress clearing any third-party rights.

There is nothing to report under this heading.

Project Resources

11. Project Partners

Explain any changes to the institutional project partners or subcontractors, and any impacts this has/will have on the project or schedule.

What other institutions or organisations are you or do you plan to collaborate with?

There are no changes to report under this heading.

Page 5 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

12. Project Management

Note any changes in project staff or their roles since the last report. Briefly explain any problems or gaps with staffing and the effect this has had on the project schedule.

There have been no changes in project staff or their roles since the last report.

13. Programme Support

Summarise contact with/influence of the programme, e.g. with the programme manager, support team, or programme-related activities.

What further support would you like from the programme, e.g. guidance, workshops, etc?

Do you have any suggestions for improving the programme?

The Project has continued to have contact with the Programme Manager and the Support Officer by email during the reporting period and has found the support to be very helpful.

Attendance at JISC meetings and other contact with the Digital Repositories Programme are noted above in Sections 6.2 and 6.3.

14. Relationships with other projects activities

Please provide a diagrammatic representation of your project’s relationships with other significant activities, such as other projects (JISC-funded or otherwise), in the UK and beyond.

This is attached as Appendix B.

15. Budget

Use the budget template to report expenditure against and attach as Appendix A. Explain the reasons for any significant overspend or underspend.

Expenditure during the reporting period is attached as Appendix A.

Page 6 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

Detailed Project Planning

16. Workpackages

Report progress against plan, noting key activities during the reporting period. Explain why any targets haven’t been met.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

Progress against plan (key activities in the current reporting period are in bold). Targets which are incomplete and overdue are in italics.

| Objective | Due date | Completion date | Comments including changes to plan needed and reasons |
| --- | --- | --- | --- |
| WP1: Project plan | September 2005 | January 2006 |  |
| WP1: Project website | September 2005 | September 2005 |  |
| WP1: Recruit Project Officer | July 2005 | July 2005 and again |  |
|  |  | in December 2005 |  |
| WP1: Write progress report for | January 2006 | February 2006 |  |
| JISC |  |  |  |

| WP1: Write progress report | July 2006 | August 2006 |  |
| --- | --- | --- | --- |
| for JISC |  |  |  |
| WP1: Project meetings | Throughout the | July, October 2005, | There is no July 2006 Project Meeting planned because the Nereus Consortium |
|  | project | January 2006, May | agreed not to meet in July. |
|  |  | 2006 | A progress report and financial report were approved by the VERSIONS |
|  |  |  | Steering Committee in Oxford, May 2006 |
| WP1: Project meetings – | Throughout the | August, November |  |
| telephone conference | project | 2005, April 2006 |  |
| WP2: Objectives for study and | October 2005 | October 2005 |  |
| questioning route for interviews |  |  |  |
| WP2: Arrange and conduct | January 2006 | February 2006 | Last remaining interviews conducted during February |
| interviews |  |  |  |
| WP2: Write up interview | January 2006 | February 2006 | Last remaining interview notes written up during February |
| notes |  |  |  |
| WP2: Interim findings report | February 2006 |  | This target has not been met because the Project Manager turned to design of |
|  |  |  | the online surveys in order to ensure that the online survey elements of the Work |

Page 7 of 16

|  |  |  | VERSIONS – Progress Report July 2006 – 0c – 16 August 2006 |
| --- | --- | --- | --- |
|  |  |  | Package did not drop too far behind schedule. Need to re-schedule this target for |
|  |  |  | September 2006 |
| WP2: Develop questionnaire | February 2006 | May 2006 | Draft questions went through several iterations and were piloted before |
| in light of interview findings |  |  | launching the survey. This activity took longer than anticipated. |
| and publications list |  |  |  |
| analysis |  |  |  |
| WP2: Launch and publicise | March 2006 | May-July 2006 | This activity went according to plan, though it took place later than |
| online questionnaire |  |  | originally scheduled because the survey design took longer than |
|  |  |  | anticipated. |
| WP2: Develop scenarios | February 2006 | March 2006 | Scenarios written and place on Project website and DRP wiki |
| from interviews |  |  |  |
| WP2: Analyse results (of | May 2006 |  | This target has not been met because the survey itself took place later than |
| online survey) including free |  |  | planned and was open until July. This activity will be carried out during August |
| text comments |  |  | 2006. |
| WP2: Report on findings of | July 2006 |  | This target has not been met because the survey itself took place later than |
| user study |  |  | planned and was open until July. This activity will be carried out during |
|  |  |  | September and October 2006. |
| WP3: Define criteria and | January 2006 | April 2006 |  |
| request publication lists |  |  |  |
| from Nereus Economists |  |  |  |
| Online partners |  |  |  |
| WP3: Analysis of proportion | February 2006 | May 2006 | This part of the analysis was undertaken from February through May. |
| of papers available in full |  |  |  |
| text |  |  |  |
| WP3: Project Team and | February 2006 | June 2006 | This part of the analysis was largely undertaken by the Project Officer. |
| Nereus EO partners provide |  |  | Non-availability of full text was not discoverable through this exercise, as |
| further information about |  |  | previously reported. |
| provenance and reasons for |  |  |  |
| non-availability |  |  |  |
| WP3: Consolidation of list | March 2006 | June 2006 |  |
| and cross-tabulation with |  |  |  |
| ROMEO listing |  |  |  |
| WP3: Analysis of findings | February 2006 | July 2006 | Tables produced from the data, exploring availability of different versions |
|  |  |  | (author final, publisher PDF) and cross-referring these by institution, |
|  |  |  | country, date of publication (pre or post 1998), and ROMEO permission. |
| WP3: Report on findings of | March 2006 |  | Analysis conducted so far forms part of a draft report. This target should be met |
| publications list analysis |  |  | by September 2006. |
| WP4: Make contact with | September 2006 | Ongoing | A preliminary list of stakeholders has been prepared and informal contacts |

Page 8 of 16

|  |  |  |  |  |  | VERSIONS – Progress Report July 2006 – 0c – 16 August 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| stakeholders |  |  |  |  | made as the opportunity arose; feedback has been sought from |
|  |  |  |  |  | stakeholders via the questionnaire and the Project workshop; links with |
|  |  |  |  |  | stakeholders have been created through participation in other activities |
|  |  |  |  |  | such as the Eprints Application Profile Working Group |
| WP4: Literature review |  | March 2006 |  |  | Literature searches have been carried out and references assembled and noted. |
|  |  |  |  |  | Compilation of the review is now underway but not yet complete. This target will |
|  |  |  |  |  | need to be re-scheduled for November 2006. |
| WP4: Draft guidelines |  | July 2006 |  |  | Target has not been met because of delays in completion of WP2 and WP3 on |
|  |  |  |  |  | which this depends. This target needs to be re-scheduled for October and |
|  |  |  |  |  | November 2006. |
| WP5: Maintain project |  | December 2006 | Ongoing |  | The Project website has been updated periodically with new deliverables, |
| website |  |  |  |  | dissemination activities and monthly informal updates. The website has |
|  |  |  |  |  | been moved to a more secure location, while maintaining the public |
|  |  |  |  |  | address: www.lse.ac.uk/versions |
| WP5: Establish mailing lists |  | October 2005 | October 2005 |  |  |  |  |  |
| WP5: Presentations and/or |  | January 2007 | Ongoing |  | See Section 19 for details |
| papers at relevant |  |  |  |  |  |  |  |  |
| workshops and conferences |  |  |  |  |  |  |  |  |
| WP5: Publish articles in |  | January 2007 | Ongoing |  | See Section 19 for details |
| appropriate journals and |  |  |  |  |  |  |  |  |
| newsletters |  |  |  |  |  |  |  |  |
| WP5: Organise and report on |  | June 2006 | July 2006 |  | Workshop was held on 10 May 2006. Notes added to Project website in |
| evaluation workshop |  |  |  |  | July. |
| Next reporting period: |  |  |  |  |  |  |  |  |
| Objective |  | Due date |  | Changes to plan needed |  |
| WP1: Project meetings |  | January 2007 |  | Ongoing |  |
| WP1: Project meetings – |  | January 2007 |  | Ongoing |  |
| telephone conference |  |  |  |  |  |  |  |  |
| WP1: Form alliances with |  | December 2006 |  | Ongoing |  |
| standards bodies and |  |  |  |  |  |  |  |  |
| stakeholders |  |  |  |  |  |  |  |  |
| WP1: Write completion report |  | January 2007 |  | Extension of target date to February 2007 |  |
| for JISC |  |  |  |  |  |  |  |  |
| WP1: Write final report for JISC |  | January 2007 |  | Extension of target date to February 2007 |  |
| WP2: Interim findings report |  | February 2006 |  | Extension of target date to September 2006 |  |
| WP2: Analyse results (of online |  | May 2006 |  | Extension of target date to August 2006 |  |

Page 9 of 16

|  |  | VERSIONS – Progress Report July 2006 – 0c – 16 August 2006 |
| --- | --- | --- |
| survey) including free text |  |  |
| comments |  |  |
| WP2: Report on findings of user | July 2006 | Extension of target date to October 2006 |
| study |  |  |
| WP3: Report on findings of | March 2006 | Extension of target date to September 2006 |
| publications list analysis |  |  |
| WP4: Literature review | March 2006 | Extension of target date to November 2006 |
| WP4: Draft guidelines | July 2006 | Extension of target date to November 2006 |
| WP4: Toolkit of guidelines | October 2006 | Extension of target date to December 2006 |
| WP4: Toolkit of guidelines on | October 2006 | Extension of target date to December 2006 |
| the website |  |  |
| WP4: Propose standards to | November 2006 | Extension of target date to January 2007 |
| JISC |  |  |
| WP5: Maintain project website | December 2006 | Continue until end of project in February 2007 |
| WP5: Presentations and/or | January 2007 | Ongoing |
| papers at relevant workshops |  |  |
| and conferences |  |  |
| WP5: Publish articles in | January 2007 | Ongoing |
| appropriate journals and |  |  |
| newsletters |  |  |
| WP5: Present results internally | January 2007 | Ongoing |
| to LSE and Nereus partners |  |  |
| WP5: Produce presentation | October 2006 | Extension of target date to January 2007 |
| materials for re-use by JISC |  |  |
| community |  |  |
| WP5: Evaluate draft toolkit | October 2006 | Extension of target date to December 2006 |
| WP5: Evaluate published toolkit | December 2006 | Extension of target date to February 2007 |

Page 10 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

17. Evaluation Plan

Report progress against plan, and note any evaluation results during the reporting period.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

Identify, as far as is possible, the measurable outcomes from the project that might reasonably be evaluated one year after the end of the project, along with the metrics that could be used to do this.

Current reporting period:

- Survey of user requirements : size of sample and range of respondents. The number of responses to the user requirements survey was 597 in total, broken down between the two separate questionnaires as follows:

|  | Researcher questionnaire |  |  |
| --- | --- | --- | --- |
|  | Total responses | 464 |  |
|  | Break down by role |  |  |
|  | Professor: | 24% |  |
|  | Lecturer / Associate Professor: | 33% |  |
|  | Post doctoral research staff: | 15% |  |
|  | Student (PhD or other research | 23% |  |
|  | degree): |  |  |
|  | Contract/freelance researcher: | 5% |  |
|  | Break down by subject |  |  |
|  | Economics | 75% |  |
|  | Accounting and Finance | 3% |  |
|  | Business and Management | 6% |  |
|  | Studies |  |  |
|  | Physics | 3% |  |
|  | Other | 13% |  |
|  | Break down by country |  |  |
|  | Austria | 7% |  |
|  | Belgium | 3% |  |
|  | Czech Republic | 4% |  |
|  | France | 6% |  |
|  | Germany | 11% |  |
|  | Italy | 5% |  |
|  | Netherlands | 9% |  |
|  | Spain | 5% |  |
|  | United Kingdom | 17% |  |
|  | United States | 12% |  |
|  | Other | 11% |  |
|  | Stakeholder questionnaire |  |  |
|  | Total responses | 133 |  |
|  | Break down by role |  |  |
|  | Library staff - directly involved | 36% |  |
|  | with repository: |  |  |
|  | Library / IT staff - technical | 10% |  |
|  | repository support |  |  |
|  | Library staff - not directly | 7% |  |
|  | involved with repository: |  |  |
|  | University senior management | 5% |  |
|  | Research funder or quality | 2% |  |
|  | agency: |  |  |
|  | Publisher or publishers' | 5% |  |
|  | organisation |  |  |
|  | Repository software community: | 5% |  |

Page 11 of 16

|  | VERSIONS – Progress Report July 2006 – 0c – 16 August 2006 |
| --- | --- |
| Library / IT standards | 2% |  |
| development - metadata, OAI: |  |  |
| Library / IT consultant: | 1% |  |
| Other (Researchers and | 20% |  |
| students) |  |  |
| Other (Miscellaneous) | 7% |  |
| Break down by repository | Note: respondents could select more than |  |
| software experience | one system |  |
| No direct knowledge of any | 49 |  |
| system |  |  |
| ARNO | 5 |  |
| CDSWare | 3 |  |
| Digital Commons | 7 |  |
| DigiTool | 3 |  |
| DSpace | 39 |  |
| Eprints | 32 |  |
| Fedora | 11 |  |
| Opus | 2 |  |
| VITAL (Fedora) | 5 |  |
| Other | 10 |  |

The number of respondents to the questionnaires was felt to be satisfactory. The response to the researcher questionnaire was overwhelmingly received from the target disciplines of economics and related subjects. The response from European researchers was very strong. The respondents to the stakeholder questionnaire were from a range of library and IT backgrounds, with a slightly higher than expected number of responses received from researchers. There was a good spread of responses from stakeholders with knowledge of different repository software systems.

- Publications list analysis: Completeness of data supplied

The key question in evaluating this activity was the availability of data. Reasonably full data was available from the partners about the publications details of their economists participating in the Economists Online Project. Only two partners were able to provide full details about provenance of full text where available. For the other partners’ publications lists details of full text availability and provenance of full text was gathered by the Project Officer by means of individual inspection of the items. In view of the scale of this task a decision was taken to concentrate on journal articles, which allowed a full set of data to be assembled for these items. From a total of over 7,000 bibliographic items, 3,118 journal articles were scrutinised in more detail, according to version of the article used, date of publication, publisher permission on self-archiving, and country in which the researcher was based. It was not possible as part of this exercise to assess the reasons for non-availability of full text. However it was considered that the user survey would address this issue in more general terms and questions were included in the survey accordingly.

- Results of user requirements survey and publications list analysis: Consensus about way forward An evaluation workshop held in May provided useful feedback on the survey design and on possible ways forward for version identification. Evaluation of the results of the survey and publications list analysis will need to be carried forward into the next reporting period.

Next reporting period:

The draft toolkit of guidelines is due to be evaluated by stakeholders for potential usefulness and quality. This will be done by circulating the draft toolkit through appropriate mailing lists and within the VERSIONS Consortium institutions and inviting feedback.

The toolkit of guidelines once published will be evaluated via email, telephone and online survey to evaluate awareness and satisfaction.

One year after the end of the project:

Measurable outcomes that could be evaluated one year after the end of the project could include:

Page 12 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

- Awareness among the JISC community of the importance of version management and identification in relation to digital repositories – awareness of the issue by librarians and IT staff could be evaluated by assessing which institutions have developed a policy on versions of papers held in their repositories.

- Researchers’ awareness of issues relating to versions and usefulness of the VERSIONS toolkit could be evaluated by monitoring page visits to the web version of the toolkit and/or by survey to assess awareness of the issues.

- Take up of this issue by stakeholders could be evaluated by assessing which repository software packages have incorporated version identification and version management features into their systems.

18. Quality Assurance Plan

Report progress against plan, describe the QA procedures put in place, and any QA results during the reporting period.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

Current reporting period:

- The online questionnaire for the user requirements study was given a pilot testing as follows: Project team and LSE Library colleagues; DRP Programme Manager; LSE economics researcher. The questionnaire design was discussed in detail during earlier iterations with VERSIONS Consortium partners by email and at a telephone conference call in April 2006. The Project team also sought feedback on the final survey design from participants at the Evaluation Workshop in May. Their comments will be taken into account when analysing the results.

- The notes of the Evaluation Workshop were circulated to participants for comment before being placed on the Project website.

- The collection of scenarios was circulated to VERSIONS Consortium partners for comment before being placed on the Project website and DRP wiki.

Next reporting period:

  - The interim findings report on the interviews will be reviewed by VERSIONS Consortium partners

  - The full findings report will be subject to peer review

  - The publications lists analysis will be subject to peer review and review by VERSIONS Consortium partners

  - The literature review will be subject to peer review

  - The guidelines on versions will be subject to peer review

  - The toolkit will be subject to peer review and evaluation

- Dissemination Plan

Report progress against plan, noting dissemination done, whether you feel it was successful, and any publicity the project received during the reporting period.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

Current reporting period:

Dissemination about the Project during the reporting period has included:

Written items:

Page 13 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

- Louise Allsop. ‘VERSIONS (Versions of Eprints - user Requirements Study and Investigation Of the Need for Standards)’. In Brief article in D-Lib Magazine (July/August 2006), 12 (7-8), In Brief. doi:10.1045/july2006-inbrief. http://www.dlib.org/dlib/july06/07inbrief.html#ALLSOP

- Project website, ongoing

- Two brief items in LSE internal publications: LSE Briefing, May 2006 and News and Views, June 2006 to publicise the surveys and raise awareness about the Project

- Publicity for the VERSIONS online survey – this constituted important dissemination about the aims of the project both to the repositories community and to researchers. The survey was publicised through the major digital repositories and OAI channels as well as to economics researchers via several key mailing lists and websites, eg Social Science Research Network (SSRN) Economics Research Network | Announcements | Other Announcements (posted 27 May 2006 and will remain for six months): http://www.ssrn.com/ern/index.html. The survey was picked up and mentioned by Peter Suber in Open Access News, for which the Project is grateful: http://www.earlham.edu/~peters/fos/2006_05_28_fosblogarchive.html

Presentations:

- Frances Shipsey. Presentation to CAB International staff on Versions of eprints: understanding researchers' needs, Wallingford, 8 Feb 2006

- Frances Shipsey. Short presentation to Legal and Policy Issues Cluster Session, JISC 2nd

Digital Repositories Programme Meeting, Warwick,	28 Mar 2006

- Frances Shipsey Presentation to SHERPA-LEAP SHERPA Liaison Meeting, University

College London,	29 Mar 2006.

Next reporting period:

The Project will aim to disseminate information about the Project through further written articles and the project website. In addition the following presentations and paper are planned:

- Frances Shipsey. Versions of academic papers and open access: attitudes and current

practice among economics researchers. Presentation at Open Scholarship 2006: New Challenges for Open Access Repositories, The University of Glasgow, 18-20 October 2006

•	Frances Shipsey. Presentation and paper at  2nd International Digital Curation Conference, Digital Data Curation in Practice, 21-22 November 2006, Hilton Glasgow Hotel, Glasgow

  - Louise Allsop. Introduction to the VERSIONS Project. ALISS Quarterly (forthcoming) For details of past and future presentations see: www.lse.ac.uk/library/versions/dissemination.html

- Exit/Sustainability Plan

Report progress against plan, noting any issues related to archiving, preservation, maintenance, supporting documentation, etc.

List objectives for the next reporting period, note if any changes to plan are needed, and explain why.

Current reporting period:

The Project website was maintained and updated during the reporting period. The site was moved over to LSE’s main web server as this was felt to be more secure than the Library server on which it was originally located.

The Project cooperated with the UK Web Archiving Consortium (UKWAC) to give permission for archiving of the Project website at: http://www.webarchive.org.uk/index.html.

Next reporting period:

There is nothing to report under this heading for the coming reporting period

Page 14 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

Appendix A. Project Budget for July 2005 to July 2006

Template for Progress Reports and Final Report

Page 15 of 16

VERSIONS – Progress Report July 2006 – 0c – 16 August 2006

Appendix B. Relationships with other projects

JISC

JISC Digital Repositories

Programme

| Eprints |  |
| --- | --- |
| Application | VERSIONS |
| Profile Working |  |
| Group | Project |
|  | LSE Library |
| Scoping Study on |  |
| Repository Version |  |
| Identification |  |
| (RIVER) |  |

JISC Scholarly

Communications

Group

Other Initiatives

SURF and DARE

Programme,

(through Nereus

Dutch partners

and Nereus

Economists

Online Project)

Nereus

Consortium –

Project

Partners

NISO/ALPSP

Working Group

on Versions of

Journal Articles

Page 16 of 16